## Data Analyst on Learn
. | WWL names | Name | ADO work item | Trophy & badge request | Scaffolding & content conversion to Learn | Add visual elements: graphics/ screen-shots | Add video (optional) | Tech reviewers | Additional Resources | Add Knowledge check | Edit | Test | Projected release date | Learn file location | Instructional Strategy / Developer Notes | Additional Notes
Learning Path | Data Preparation | Bring AI to your business with AI Builder |  | 184962
Module | Get Data from Different Data Sources | Get started with AI Builder |  | 184946 | [8 empty] | 3 Mar, 2020
Module | Identify and connect to a data source | Manage models in AI Builder |  | 184957 | [8 empty] | 3 Mar, 2020
Learning Path | Change data source settings | Improve business performance with AI Builder
Module | Select a shared dataset or create a local dataset | Get started with form processing |  | 184958 | [8 empty] | 3 Mar, 2020
Module | Select a storage mode | Get started with text recognition |  | 187062 | [7 empty] | 193421
Module | Choose an appropriate query type | Get started with sentiment analysis | [9 empty] | 193425
Module | Write an appropriate language query | Get started with business card reader | [9 empty] | 193427
Module | Identify query performance issues | Get started with object detection |  |  | waiting on images
Module | Optimize query performance | Get started with language detection | [9 empty] | 193429
Module | Use the Common Data Service (CDS) | Get started with key phrase extraction | [9 empty] | 193432
Learning Path | Use parameters | Administer AI Builder
Module | Create a custom connector | Get started with AI Builder licensing
Module |  | TBD
Learning Path |  | Go further improving your business with AI Builder
Module | Profiling the Data | Automate tracking of shipments
Module |  | Advanced predition scenario (tbd) |  |  | waiting on images